Anticipating obstacles:

It was invaluable to anticipate any potential barriers that could be encountered during Implementation and imperative to create a strategy to overcome the challenge.  The hurdles to our comprehensive strategy that were anticipated and addressed are described in Table 1.

| Anticipated Obstacles | Safer Recommendations |
| --- | --- |
| Implicit assumption that “target” is high-risk drinkers | Based on the “prevention paradox” where moderate and infrequent binge drinkers cause more problems since there are that many more of them (Weitzman and Nelson, 2004) and lower-risk drinkers are most likely influenced by alcohol control measures. |
| Ambivalence about student drinking | Countering the Amethyst Initiative arguments with data on lives saved through Increasing the drinking age to 21. |
| Low perceived efficacy of environmental preventive interventions | Survey of UC Berkeley students (Saltz, 1998) indicates that respondents have a higher perception of the effectiveness of alcohol policies than they thought their peers would. |
| Challenges of coordination and resources allocation | Establishing a focus on off-campus parties provided an effective and efficient way to redistribute existing resources rather than being reactionary. |
| Possible fears of backlash (especially when enforcement is involved) | The issue was framed as one of student safety and avoidance of the consequences related to intoxication. |
| Preference for persuasion over control | Through laying out a comprehensive implementation strategy with a select group of stakeholders to obtain commitment to the project |
| Prevention staff usually lack the authority to launch initiatives | Provided an implementation framework to build institutional and community support and commitment for the project |

Table 1.  Anticipating Obstacles and Recommendations